MSHA - Status Report

| Date: | 02/03/06 |
| --- | --- |
| Attendees: | Jennifer Cochran, Hong Li, Shawn Sullivan, Craig Wiggins, Betty Wilkins, Paula Johnson Williams |

Accomplishments

- Synthesized additional data for PA presentation

- Made PA presentation

- Moved templates to new website

- Worked on observation checklists

- Reviewed design approach

- Created questions to ask mine supervisors during mine visit

- Reviewed and gathered materials to take to mine

- Mine visit canceled

Next Week’s Goals

- Complete observation checklists

- Send condensed, generic version of JTA to SMEs

- Completed PA document due

- Review design approach