T/TAC Mission 6: VA Assessment

Weekly Status Report

Dates: November 4, 2005 – November 11, 2005

Team Members: Matt Humphrey, Aala’a Mashaal, Pamela Sharpe, Tim Smith, and Maria Washington

A                               D                                   D                         I                         E

Our Current Situation

The Needs Analysis has been completed and presented. The feedback received from Kevin to restructure the document to a more coherent structure will be implemented.  We are now moving into the task analysis phase of the project.

Accomplishments

- Received surveys from T/TAC training in Fredericksburg

- Compiled the data with the previously gathered data and analyzed the survey data creating statistical charts

- Interviewed Kay Klein of T/TAC GMU (and spoke to her over the phone)

- Finished needs analysis document

- Presented needs analysis in Dr. Clark’s class

- Devised a work strategy for the task analysis

Action Items

- Work on task analysis

  - Analyze the procedure manual

  - Talk to Kay Klein for lead on task analysis

  - Create initial analysis of creating a lesson plan document

- Begin thinking about compilation of all documents for a final coherent treatment document

- Incorporate feedback from each document and make necessary corrections that Kevin or peers suggested