T/TAC Mission 6: VA Assessment

Weekly Status Report

Dates: October 28, 2005 – November 4, 2005

Team Members: Matt Humphrey, Aala’a Mashaal, Pamela Sharpe, Tim Smith, and Maria Washington

A                               D                                   D                         I                         E

Our Current Situation

The learner analysis has been completed and presented. We are now moving into the needs assessment phase of the project.

Accomplishments

- Finished learner analysis document

  - Compiled observations

  - Synthesized survey results

  - Revised personas

- Presented learner analysis to class in Dr. Clark’s class

- Devised a work strategy for the needs analysis and task analysis phases

Action Items

- Send lesson plan document to Shuangbao to post on T/TAC Online

- Revisit the PA plan for needs assessment guidance

  - Flesh out the next steps section

- Analyze survey results

- Continue data gathering

- Create interview instrument

- Follow up on request for teacher contact info (survey distribution)