T/TAC Mission 6: VA Assessment

Weekly Status Report

Dates: September 26, 2005 - September 30, 2005

Team Members: Matt Humphrey, Aala’a Mashaal, Pamela Sharpe, Tim Smith, and Maria Washington

A                               D                                   D                         I                         E

Our Current Situation

We are in the analysis phase of the project preparing to present our Performance Analysis so we can begin a thorough needs analysis.

Accomplishments

- Had an interview with Mary Wilds, one of our Subject Matter Experts

- In the iterative process of refining our Performance Analysis

- Attended the VAAP training in the Hyatt in Fair Lakes

- Analyzed the Results of the survey

- Wrote follow up letter for both John and Mary including

  - Background

  - Problem

  - Proposed Solution

  - Summary of Discussion Items

  - Action Items

- Had Kevin review our PA and Follow-up letter for feedback and adjusted them accordingly

Action Items

- Work on finalizing the Performance Analysis

- Create PowerPoint presentation of the Performance analysis and prepare for presentation on October 6

- Send follow up letter to the clients (John and Mary) after sending to Mike for review

- Add documents that have been completed to the project website