T/TAC Mission 6: VA Assessment

Weekly Status Report

Dates: January 23 – January 27, 2006

Team Members: Matt Humphrey, Aala’a Mashaal, Pamela Sharpe, Tim Smith, and Maria Washington

A                               D                                   D                         I                         E

Our Current Situation

The team came back from winter break, met with Mike Behrman to review the status of the project.  The team is in the development phase of the EPSS.

Accomplishments

- Quick overview of final presentation to Dr. Clark

- Created Spring “06” project site

- Met with Dr. Behrman to discuss revisions to Performance Analysis

- Met with Shuangbao to review prototype

- Began revisions to Performance Analysis and Needs Analysis

Action Items

- Meet with clients to discuss design approach and prototype

- Review Shuangbao’s development of the EPSS

- Complete revisions to Performance Analysis and Needs Analysis